## README
WasteWatch / Civilytics — ticket backlog
Scope of this file | Login and Landing (Live Monitoring) only. Remaining pages to follow.
Generated | 2026-10-07
Status values | Done = implemented and verified. Open = not started.
Type values | Feature / Bug / Gap / Security / Chore
Gap vs Bug | Bug = built and wrong. Gap = never built, and its absence is a defect.
Priority | P0 blocks release. P1 before client demo. P2 after.
Evidence | Every row cites a file:line or a verification command. Nothing here is inferred.
Counts | Login 14 ¦ Landing 28 ¦ total 42

## Login
Ticket ID | Module | Page | Feature | Type | Title | Description | Acceptance Criteria | Priority | Estimate | Depends On | Evidence / Source | Status
WW-LGN-001 | auth | Login | Branded sign-in form | Feature | Civilytics-branded login form with server-side token exchange | Own form rather than Keycloak's hosted page. Credentials POST to /api/auth/login; the backend exchanges them with Keycloak and sets httpOnly cookies. | Form shows hex brandmark, 'Civilytics', 'Satyaki Solutions Pvt Ltd' byline, Username + Password fields, Sign in button. No token is readable from JavaScript (document.cookie excludes ww_access). | P0 | Done | - | frontend/src/pages/Login.tsx; backend/app/api/routes/auth.py | Done
WW-LGN-002 | auth | Login | Submit button gating | Feature | Sign in disabled until both fields are non-empty | Button carries disabled={submitting ¦¦ !username ¦¦ !password}. | Button disabled on load; enabled only when both fields have content; disabled again while a request is in flight. | P2 | Done | WW-LGN-001 | Login.tsx:100 | Done
WW-LGN-003 | auth | Login | Submitting state | Feature | Spinner and 'Signing in…' label during submit | Both inputs disable while submitting so a second submit cannot race the first. | On submit, label reads 'Signing in…', a spinner shows, both inputs are disabled. | P2 | Done | WW-LGN-001 | Login.tsx:100-104 | Done
WW-LGN-004 | auth | Login | Error surface | Feature | Failed sign-in shows an inline alert | Error container carries role='alert' so it is announced by screen readers. | Wrong credentials render the alert with an identical message for unknown-user and wrong-password. Message does not reveal which was wrong. | P0 | Done | WW-LGN-001 | Login.tsx:92 | Done
WW-LGN-005 | auth | Login | Account enumeration | Security | Identical failure message for unknown user and wrong password | Backend returns the same 401 detail for both, and logs the Keycloak status without the body (error bodies echo the username). | Responses for an unknown username and a wrong password are byte-identical in status, body and timing class. | P0 | Done | WW-LGN-001 | auth.py::_exchange | Done
WW-LGN-006 | auth | Login | Session restore | Feature | Existing session skips the login page | AuthProvider calls GET /api/auth/me on load; 200 renders the dashboard, 401 renders Login. | Reloading with a valid cookie lands on the dashboard without re-entering credentials. No login flash. | P1 | Done | WW-LGN-001 | context/AuthContext.tsx | Done
WW-LGN-007 | auth | Login | Silent token refresh | Feature | 401 on any API call triggers one refresh then one retry | Global fetch interceptor; AUTH_FAILED_EVENT dispatched if the retry still 401s. | A request made after the 15-minute access cookie expires succeeds transparently. Only one refresh is attempted per failure. | P1 | Done | WW-LGN-006 | lib/api-client.ts | Done
WW-LGN-008 | auth | Login | Logout control | Gap | No way to sign out anywhere in the UI | POST /api/auth/logout exists and revokes the refresh token at Keycloak, but no component calls it. useAuth() is not imported by a single component. A signed-in operator on a shared workstation cannot end their session. | Sign-out sits in the bottom-left sidebar block, under the clock, alongside the signed-in user. Calls POST /api/auth/logout, clears both cookies, returns to Login. Reachable from all seven views since Sidebar is in MainLayout. | P0 | 4h | WW-LGN-001 | grep: no useAuth() consumer in components/; Sidebar.tsx:228-246 footer is clock + powered-by only | Open
WW-LGN-009 | auth | Login | Signed-in identity | Gap | The UI never shows who is signed in | No username, role or avatar is rendered. An operator cannot tell whose session they are acting under, which undermines every acknowledgement attribution. | Bottom-left sidebar block shows username and role, above the clock. Visible in all seven views. Role badge distinguishes owner / admin / viewer. | P1 | 3h | WW-LGN-008 | Sidebar.tsx:228-246 renders TimeDisplay + powered-by, no identity | Open
WW-LGN-010 | auth | Login | Session expiry notice | Gap | Expired session redirects with no explanation | AUTH_FAILED_EVENT returns the user to Login silently. They cannot tell whether they were logged out, lost network, or the server failed. | On auth failure the Login page shows 'Your session expired. Please sign in again.' and the event is logged server side. | P2 | 2h | WW-LGN-007 | lib/api-client.ts AUTH_FAILED_EVENT | Open
WW-LGN-011 | auth | Login | Password reset path | Gap | Copy says contact your administrator; no in-app path | Direct Access Grant has no self-service reset. POST /api/users/{id}/setup-email is the reset path but there is no UI for it. | Admin can trigger a reset email for a user they manage from User Management. Login copy points at that flow. | P2 | 3h | WW-USR-004 | Login.tsx:106; users.py::resend_setup_email | Open
WW-LGN-012 | auth | Login | Responsive layout | Gap | Login has zero responsive breakpoints | No sm:/md:/lg: utilities in Login.tsx. Uses h-screen, which clips on mobile browsers where 100vh includes the URL bar. | Usable at 375px with a 16px gutter and no horizontal scroll. h-dvh replaces h-screen. | P1 | 3h | - | grep: 0 responsive prefixes in Login.tsx | Open
WW-LGN-013 | auth | Login | Test hooks | Chore | Add data-testid attributes for Playwright | Inputs have ids and labels so getByLabel works, but the brandmark, error alert and submit state have no stable hook. | data-testid on form, error alert, submit button and brandmark. Accessible-role selectors remain primary. | P2 | 2h | - | Login.tsx | Open
WW-LGN-014 | auth | Login | Keycloak realm prerequisites | Chore | Document and verify realm setup required for login to work at all | Direct Access Grants are off by default on new clients; realm roles must be COMPOSITE owner->admin->viewer or require_role rejects an owner. | A fresh realm import produces a working login for owner, admin and viewer. Covered by keycloak/realm-test.json. | P0 | Done | - | keycloak/realm-test.json | Done

## Landing
Ticket ID | Module | Page | Feature | Type | Title | Description | Acceptance Criteria | Priority | Estimate | Depends On | Evidence / Source | Status
WW-LND-001 | dashboard | Landing (Live Monitoring) | Default view | Feature | Dashboard opens on Live Monitoring | Index renders MonitoringView when currentView === 'monitoring', the initial state. | After sign-in the camera grid is visible without further navigation. | P0 | Done | WW-LGN-001 | pages/Index.tsx; MonitoringContext.tsx:177 | Done
WW-LND-002 | dashboard | Landing | Camera grid | Feature | Camera tiles in a selectable grid layout | CameraGrid renders a tile per camera; layout switches via TopBar (default 3x3). | Grid renders one tile per camera from GET /api/cameras. Layout control changes tile count and persists for the session. | P0 | Done | WW-LND-001 | components/camera/CameraGrid.tsx; TopBar.tsx:40 | Done
WW-LND-003 | dashboard | Landing | Live video | Feature | Each tile plays its camera over WebRTC | WebRTCPlayer negotiates WHEP against MediaMTX. | A tile for an online camera shows moving video within 5s. An offline camera shows a placeholder, not a black box. | P0 | Done | WW-LND-002 | components/camera/WebRTCPlayer.tsx | Done
WW-LND-004 | dashboard | Landing | Default grid on mobile | Gap | 3x3 default means nine simultaneous WebRTC streams | gridLayout defaults to '3x3'. On a phone this is a thermal, battery and decoder-limit failure, not a layout problem. | On viewports under 768px the grid falls back to one stream plus a camera list. Desktop default unchanged. | P0 | 6h | WW-LND-002 | MonitoringContext.tsx:26 | Open
WW-LND-005 | dashboard | Landing | Violation highlight | Feature | Tile highlights on violation, blue on hover | Panels must visually distinguish a violating camera from a hovered one. | A camera with an active critical alert renders a persistent violation border. Hover renders blue. The two are distinguishable when both apply. | P1 | 4h | WW-LND-002 | findings-dashboard-highlighting.md | Open
WW-LND-006 | dashboard | Landing | Violation border never renders | Bug | Tailwind layer precedence stops the violation border painting | The violation border utility is overridden by a component-layer rule, so the class is applied but has no visual effect. | Violation border is visible on an alerting tile at all grid sizes. Regression-tested with a screenshot assertion. | P1 | 3h | WW-LND-005 | findings-dashboard-highlighting.md | Open
WW-LND-007 | dashboard | Landing | Sidebar navigation | Feature | Seven-item sidebar switches views | Items: Live Monitoring, Camera Map, Analytics, Event History, Timeline Playback, Camera Management, Settings. | Each item switches the main panel and shows an active state. | P0 | Done | WW-LND-001 | components/layout/Sidebar.tsx:34-40 | Done
WW-LND-008 | dashboard | Landing | Role-gated navigation | Gap | A viewer sees Camera Management and Settings and gets 403s | No can('admin') gate on sidebar items. Permission is discovered by failure. | Admin-only items are hidden or disabled with a reason for a viewer. Backend remains the authority. | P0 | 4h | WW-LGN-009 | Sidebar.tsx has no role check | Open
WW-LND-009 | dashboard | Landing | Active alert badge | Feature | Sidebar shows a count of active alerts | activeAlerts = alerts.filter(a => a.status === 'active').length rendered as a destructive badge. | Badge shows the active count and disappears at zero. | P1 | Done | WW-LND-007 | Sidebar.tsx:55,168 | Done
WW-LND-010 | dashboard | Landing | Alert panel | Feature | Slide-in panel lists active alerts from any view | AlertPanel mounts in MainLayout, so it is reachable from all seven views. | Bell toggles the panel. Panel lists active alerts newest first with severity, camera and time. | P0 | Done | WW-LND-009 | MainLayout.tsx:34 | Done
WW-LND-011 | dashboard | Landing | Alert panel blocks the app | Bug | Auto-opening panel renders a full-screen backdrop over everything | MainLayout renders fixed inset-0 behind the panel, and MonitoringContext opens it on every critical/warning alert, rate-limited only to 1 per 3s. Mid-ROI-edit this steals the screen repeatedly. | Incoming alerts do not steal focus or block interaction. Panel opens without a blocking backdrop, or auto-open becomes a non-modal toast with a click-through to the panel. | P0 | 4h | WW-LND-010 | MainLayout.tsx:28; MonitoringContext.tsx:128 | Open
WW-LND-012 | dashboard | Landing | Acknowledge alert | Feature | Operator acknowledges an alert from the panel | PATCH /api/alerts/{id}, require_viewer. | Acknowledging removes it from the active list and records who and when. | P0 | Done | WW-LND-010 | MonitoringContext.tsx:191; routes/alerts.py | Done
WW-LND-013 | dashboard | Landing | Acknowledgement is not attributed | Bug | alerts table has no acknowledged_by until migration 009 | The UI acknowledges ALERTS, and that table had no attribution columns. Columns now exist; the route does not populate them. | PATCH /api/alerts/{id} writes acknowledged_by from the token, acknowledged_at, and ack_source='dashboard'. | P0 | 3h | WW-LND-012 | migration 009; routes/alerts.py | Open
WW-LND-014 | dashboard | Landing | Acknowledgement does not broadcast | Bug | Other operators keep seeing an acknowledged alert | No WebSocket broadcast on acknowledge; peers update only on their next 5s poll, so two operators work the same alert. | Acknowledging pushes to /ws/alerts and all connected dashboards update within 1s. | P1 | 4h | WW-LND-012 | routes/alerts.py has no broadcast | Open
WW-LND-015 | dashboard | Landing | Clear all notifications | Bug | Viewer sees a control that calls an admin-only endpoint | Sidebar renders a clear-all button for any role; POST /api/alerts/clear is require_admin, so a viewer gets a 403 with no explanation. | Control is hidden for a viewer, or the endpoint is re-scoped deliberately. Role and control agree. | P1 | 2h | WW-LND-008 | Sidebar.tsx:179-190; routes/alerts.py | Open
WW-LND-016 | dashboard | Landing | Duplicate alert transport | Bug | Alerts arrive over both a WebSocket and a 5s poll | useAlerts holds /ws/alerts while MonitoringContext polls GET /api/alerts every 5s. The poll, not the socket, drives notification and panel auto-open. | One transport is authoritative. The socket pushes; the poll becomes a slow reconciliation or is removed. | P1 | 4h | WW-LND-010 | useAlerts.ts:125; MonitoringContext.tsx:140 | Open
WW-LND-017 | dashboard | Landing | Alert sound toggle | Feature | Operator can mute alert audio | Sidebar toggle with an ON/OFF indicator. | Toggle silences audio for new alerts and the state survives a view switch. | P2 | Done | WW-LND-010 | Sidebar.tsx:199-215 | Done
WW-LND-018 | dashboard | Landing | Zone filter is hardcoded | Bug | TopBar zone dropdown lists prototype values | Items are literal strings 'Zone A - Industrial' … 'Zone D - Highway', not data. They match no zone in the database and filter nothing. | Dropdown is populated from the zones table scoped to the caller's tenant, and selecting one filters the grid. | P1 | 4h | WW-LND-002 | TopBar.tsx:80-84 | Open
WW-LND-019 | dashboard | Landing | Status filter is hardcoded | Bug | TopBar status dropdown is not wired | Items are static and do not filter the grid. | Selecting a status filters tiles by cameras.status. | P1 | 2h | WW-LND-018 | TopBar.tsx:96-100 | Open
WW-LND-020 | dashboard | Landing | Camera offline is silent | Bug | Camera loss is written to the DB and never pushed | CameraStatusConsumer updates cameras.status and broadcasts nothing, so the dashboard learns on the next 15s poll and nobody is alerted. | Camera loss raises a dashboard alert and pushes over WebSocket. Reconnection clears it. | P0 | 6h | WW-LND-003 | services CameraStatusConsumer | Open
WW-LND-021 | dashboard | Landing | Silent 401 renders zeros | Bug | A failed fetch shows an empty dashboard rather than an error | Callers treat a non-200 as empty data, so an auth or server failure looks like 'no events'. | A failed load shows an error state with a retry, distinct from a genuinely empty result. | P0 | 4h | WW-LGN-007 | lib/api-client.ts | Open
WW-LND-022 | dashboard | Landing | First-run empty state | Gap | A fresh install shows an empty grid with no guidance | No cameras exist on first boot and nothing tells the operator what to do. | Empty grid shows an 'Add your first camera' CTA routing to Camera Management with the add dialog open. Hidden for a viewer. | P1 | 3h | WW-LND-008 | plan-camera-onboarding.md | Open
WW-LND-023 | dashboard | Landing | Responsive layout | Gap | Landing has zero responsive breakpoints | MonitoringView, Sidebar, MainLayout and AlertPanel contain no sm:/md:/lg: utilities. Sidebar is a fixed w-56 (224px) with no collapse, 60% of a 375px screen. MainLayout uses h-screen. | Sidebar becomes a drawer under 768px. h-dvh replaces h-screen. No horizontal scroll at 375px. | P0 | 8h | WW-LND-004 | grep: 0 responsive prefixes | Open
WW-LND-024 | dashboard | Landing | No URL for any view | Gap | Seven views behind one route, so nothing is linkable | Everything under Index is currentView state. No deep link, no bookmark, no back button; a refresh always returns to monitoring. | Each view has a path. Browser back works. An operator can send a colleague a link to what they are looking at. | P1 | 8h | WW-LND-007 | App.tsx has a single '/' route | Open
WW-LND-025 | dashboard | Landing | Pin a camera | Feature | Pinned cameras sort first in the grid | cameras.is_pinned, ordered is_pinned DESC, name. | Pinning moves a tile to the front and survives reload. | P2 | Done | WW-LND-002 | routes/cameras.py::list_cameras | Done
WW-LND-027 | dashboard | Landing | Sidebar clock leaks its interval | Bug | TimeDisplay uses useState where useEffect was meant | useState(() => { const i = setInterval(...); return () => clearInterval(i); }) — the initializer runs once and its RETURN VALUE is stored as state, so the cleanup is never called and the interval leaks on unmount. Under StrictMode in dev it creates two intervals. It appears to work because setInterval still fires. | Clock uses useEffect with a cleanup. One interval per mount, cleared on unmount. Verified with a mount/unmount test asserting no pending timers. | P2 | 1h | - | Sidebar.tsx:250-256 | Open
WW-LND-028 | dashboard | Landing | Clock date uses en-US locale | Bug | Date renders in US format for an Indian deployment | toLocaleDateString('en-US', ...) is hardcoded. Time is correctly hour12:false (24-hour), matching TL5, but the date reads 'Oct 7, 2026' rather than the local convention. | Date uses en-IN or the browser locale. Time stays 24-hour. | P2 | 1h | WW-LND-027 | Sidebar.tsx:263-269 | Open
WW-LND-026 | dashboard | Landing | Test hooks | Chore | Add data-testid to grid, tiles, sidebar items and alert panel | No stable hooks for Playwright; tile identity currently depends on text content. | data-testid on camera-grid, camera-tile-{id}, nav-{view}, alert-panel, alert-item-{id}, sidebar-user, sidebar-logout, sidebar-clock. | P2 | 3h | - | - | Open